## Overview
This template will assist you in creating a DMAIC-based project charter.
This short, formal document is part of the PM toolkit, designed to help you articulate, define, and present to stakeholders how this effort will support the realization of your portfolio goals, and the wider corporate strategy.
Within you’ll find:
An explanation of why the project is needed, establishing clarity of purpose from the start
Detailed objectives, ensuring there are clear targets and milestones to work towards in the project
Anticipated constraints in delivering the objectives and how you plan to overcome and monitor
The key stakeholders, meaning you can build out an engagement plan to communicate and deliver value in their eyes
Scoping of the project’s boundaries, including basics around the start and end date, items to be addressed, and fringe items which will not be addressed
The potential risks in your project, giving a view to all potential risks that may appear in the delivery of the work, accompanied by a risk register and management plan to assign owners and actions for overcoming these hurdles should they appear
Anticipated benefits of delivering the project should be provided, tailored to sponsors, stakeholders and those that feed into objectives beyond this project
Project costs which lead into a budget, a rough estimate of the cost in delivering the project and who is the budget holder
To maximize the value of your project, be sure to visit our Continuous Improvement resource center for a comprehensive collection of content around driving your business towards its ultimate destination - business excellence - or click below to book a chat with a member of our team to talk through your challenges.

## Template
Project charter
Prepared by: | Sponsor: |  |  | Date:
Project Name
Project Sponsor(s)
Project Manager
Email
Phone
Business Unit
Process Impacted
Start Date
Finish Date
Estimated Savings
Estimated Costs
Green Belts Used
Black Belts Used
What is the issue at hand, the goals, objectives and deliverables?
Issue
Purpose or Problem Statement
Business Case
Goal Statement
Metrics
Deliverables
Project scope and anticipated schedule
In scope
Out of scope
Anticipated schedule | Milestone |  | Start | Finish
Form project team
Prelim review
Project scoping
Finalize plan and charter
Kick off session
DMAIC steps:
1. Define
2. Measure
3. Analyze
4. Improve
5. Control
Project summary report
Project learnings session
Project close
Required resources and costs | Name | Role | % Time
Project Team
Resources to support
Subject matter expert(s)
Types of cost (direct, indirect, fixed, variable, sunk) | Supplier | Unit costs | Quantity | Total
Contractors (direct) |  |  |  | 0
Software licences (direct) |  |  |  | 0
Office space (indirect) |  |  |  | 0
Agile consultancy (fixed) |  |  |  | 0
etc. |  |  |  | 0
Total costs |  |  |  | 0
Project benefits and how this delights your customer (internal / external)
Process owner
Key stakeholders
Final, delighted customer
Expected benefits
Benefit types | KPI | Baseline (jump off point) | Goal | Estimated benefits
-
Total annual value of benefits |  |  |  | 0
Project risks, constraints and assumptions
Risks
Assumptions
Issues
Dependencies

## Example
Project charter
Prepared by: Owen Holms | Sponsor: Olga Jensen |  |  | Date: 11/02/2022
Project Name | Manufacturing shop floor yield improvement
Project Sponsor(s) | Daniel Bluhm, VP, Sustainable Automobile Division | Olga Jensen, Head of Business Excellence
Project Manager | Owen Holms
Email | owen.holms@acmecorp.com
Phone | 49 23 456 789
Business Unit | Electric Automobiles
Process Impacted | New business development | Vehicle delivery
Start Date | 2022-09-01
Finish Date | 2023-12-31
Estimated Savings | 1260000
Estimated Costs | 119250
Green Belts Used | David Schultz | Jurgen Kahn | Alex Wright | Bernadette Jonson
Black Belts Used | Olga Jensen | Marcelo Olsen | Sebastien Svenson | Johan Blomqvist
What is the issue at hand, the goals, objectives and deliverables?
Issue | Sales orders are c.4k below industry levels | Delivery dates are missed 21% of the time
Purpose or Problem Statement | Drive greater revenue rates | Delight our customers, increasing loyalty and upsell opportunity
Business Case | Our target to generate $2m. revenue through this product line is being missed - revenue increase and cost savings through improving our processes can help us bridge this gap
Goal Statement | Generate more product line sales per customer | Increase average order size by $7000 per month (from $3000 to $10000) by May 30 2023
Metrics | Orders per month | Average order size
Deliverables | Project scoping | Project timeline | Project report | Replicable learnings
Project scope and anticipated schedule
In scope | Analyzing sales data from the last 18 months and in-person observations
Out of scope | Analyzing sales data from outside of this product line
Anticipated schedule | Milestone |  | Start | Finish
| Form project team |  | 2022-09-01
| Prelim review |  | 2022-09-24 | 2022-09-30
| Project scoping |  | 2022-10-02 | 2022-10-07
| Finalize plan and charter |  | 2022-10-10 | 2022-10-20
| Kick off session |  | 2022-11-01
| DMAIC steps: |  | 2022-11-14 | 2023-04-21
| 1. Define |  | DATE | DATE
| 2. Measure |  | DATE | DATE
| 3. Analyze |  | DATE | DATE
| 4. Improve |  | DATE | DATE
| 5. Control |  | DATE | DATE
| Project summary report |  | 2023-05-01 | 2023-05-10
| Project learnings session |  | 2023-05-17 | 2023-05-18
| Project close |  | 2023-05-30
Required resources and costs
Project Team | Dortmund Group 1 | Dortmund Group 2
Resources to support | $125,000 budget | 15 project team members | Software package | Room hire
Subject matter expert(s) | Olga Jensen | Dan Costa | Henrik Lowe
Types of cost (direct, indirect, fixed, variable, sunk) | Supplier | Unit costs | Quantity | Total
Contractors (direct) | HelpingHanz | 5000 | 20 | 100000
Software licences (direct) | Software CorpX | 80 | 40 | 3200
Office space (indirect) | WiWorx | 350 | 3 | 1050
Agile consultancy (fixed) | AgileCrew | 1500 | 10 | 15000
etc. |  |  |  | 0
Total costs |  |  |  | 119250
Project benefits and how this delights your customer (internal / external)
Process owner | Dan Costa
Key stakeholders | Dan Costa | Daniel Bluhm | Henrik Lowe
Final, delighted customer | Eliza Electric - electric car buyer segment
Expected benefits
Benefit types | KPI | Baseline (jump off point) | Goal | Estimated benefits
Increased orders (monthly) | Orders per sales person | 30 | 45 | 45 orders per month
Higher average order amount (monthly) | Revenue per order | $23000 | $30000 | $7000
Improved on time delivery | -
etc.
Total annual value of benefits |  |  |  | 1260000
Project risks, constraints and assumptions
Risks | Resource availability | Conflict with on-going transformation programs | Efficiences do not result in increase orders and / or ordersize
Assumptions | Previous projects in similar areas can be applied | Resources can be ringfenced
Issues | Cost - should ROI be unobvious | Previous project learnings are not transferrable
Dependencies | This project is dependent on resources being available 100% of Define, Measure and Analyze phases

## AP Schedule_1 (hidden)
Core Objectives: Sales (k€)/ FTE ENNIS line from 192 to 202 by Dec. Yr 1 OEE ENNIS line from 74% to 85% by Dec Yr 1 Setup-Time Reduction ENNIS line from 30 min to 15 min by Dec. Yr 1 |  |  | Timeline | [11 empty] | Target Improvement
|  |  |  | = Original Plan |  |  |  | X | = Progress at Review
Year
Action Steps / Kaizen Events | Owner | Planned Dates | [12 empty] | Status (Past Due in Red) | Impact
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. Kaizen Event - Just in Time | Prod Mgr | Jan - w1 | bar: Jan
2. Kaizen Event - Daily Kaizen | Prod Mgr | Jan - w3 | bar: Jan
3. Kaizen Event - OEE | Proc Eng | Feb - w1 | bar: Feb
4. Kaizen Event - Auto Quality | Qual Eng | Feb - w3 | bar: Mar
5. Kaizen Event - Problem Solving | Prod Mgr | Mar - w3 | bar: Mar
6. Kaizen Event - Just in Time | Prod Mgr | Apr - w3
7. Kaizen Event - Poka Yoke | Eng Mgr | Jun - w1
8. Kaizen Event - Daily Kaizen | Prod Mgr | Jun - w3
9. Kaizen Event - SMED | Proc Eng | Jul - w1
10. Kaizen Event - Standard Work | Proc Eng | Jul - w3
11. Kaizen Event - SMED | Proc Eng | Oct - w1
12. Kaizen Event - OEE | Proc Eng | Nov - w1
Note on D5: Melissa La Gana: Will this be actual names?
Note on R5: Melissa La Gana: Combine Status and Impact. Red font of Impact will indicate past due
Note on D7: Melissa La Gana: Make this an email link for easy emailing to owner

## AP Schedule_2 (hidden)
1. Kaizen Event - Just in Time | Jan - w1
2. Kaizen Event - Daily Kaizen | Jan - w3
3. Kaizen Event - OEE | Feb - w1
4. Kaizen Event - Auto Quality | Feb - w3
5. Kaizen Event - Problem Solving | Mar - w3
6. Kaizen Event - Just in Time | Apr - w3
7. Kaizen Event - Poka Yoke | Jun - w1
8. Kaizen Event - Daily Kaizen | Jun - w3
9. Kaizen Event - SMED | Jul - w1
10. Kaizen Event - Standard Work | Jul - w3
11. Kaizen Event - SMED | Oct - w1
12. Kaizen Event - OEE | Nov - w1
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec